IWIRC New Network Checklist

A Step-by-Step Guide for Members Starting a New IWIRC Network

Updated May 2026  •  Questions? Contact ccschnapp@iwirc.com or sfarmer@iwirc.com

How to Use This Checklist: This checklist walks you through the full lifecycle of establishing a new IWIRC network — from initial interest-gathering through your first year of operation. Items marked with ☐ are action steps. Italicized notes provide guidance or context. Work through each phase in order and coordinate with IWIRC at each approval gate.

| PHASE 1 | Gauging Interest & Building Your Founding Group | Weeks 1–4 |
| --- | --- | --- |

Step 1: Assess Local Demand

☐  Identify your geographic focus area (city, region, or country) and confirm no existing IWIRC network covers it.

→  Check the full network map at iwirc.com/networks. If a nearby network exists, consider whether a new network is warranted or whether joining the existing one makes more sense.

☐  Survey colleagues informally — attorneys, bankers, accountants, turnaround managers, financial advisors — to gauge interest.

☐  Identify a minimum of four (4) individuals committed to joining IWIRC and helping launch the network.

→  Four members is the required minimum to apply; a founding group of 8–12 is recommended for a strong start.

☐  Research the local insolvency and restructuring market: key firms, practitioners, relevant bar associations, and professional organizations.

☐  Consider whether any existing professional associations in your area could be natural partners or referral sources for membership.

Step 2: Hold an Exploratory Gathering

☐  Organize an informal gathering (lunch, coffee, cocktails, etc.) with interested colleagues.

→  Share IWIRC’s mission: connecting, promoting, and advancing women in insolvency and restructuring worldwide.

☐  Present the benefits of IWIRC membership (visit iwirc.com/membership for the full list), including:

→  Access to 2,400+ global members across 58+ networks on 6 continents.

→  Referral network, mentoring, career resources, and leadership opportunities.

→  Speaking bureau, award programs (Woman of the Year, Founders’ Award), and professional directory.

→  Webinars, conferences, and networking events at local, regional, and international levels.

☐  Discuss the responsibilities of founding members, including board service, dues, and event planning.

☐  Collect expressions of interest and contact information from attendees.

☐  Follow up with attendees within one week to confirm founding commitments.

| PHASE 2 | Regulatory Review & Application Preparation | Weeks 3–8 |
| --- | --- | --- |

Step 3: Confirm Local Legal Requirements

☐  Verify with local government or counsel whether any approvals, registrations, or filings are required to operate a nonprofit professional association in your jurisdiction.

→  U.S.-based networks generally do not require additional governmental approvals beyond IWIRC’s internal steps. Non-U.S. jurisdictions may require additional paperwork — check local nonprofit or association law.

☐  If outside the U.S., confirm whether a local entity (e.g., incorporated association, chapter of a foreign nonprofit) must be formed.

☐  If forming a local entity, engage local legal counsel to advise on entity type, registration, and ongoing compliance obligations.

☐  Note any restrictions on the use of the IWIRC name or brand under local law.

Step 4: Prepare Your Application

☐  Download the Network Proposal template from the IWIRC website Resources/Documents section.

☐  Complete the Network Proposal, including:

→  Proposed network name and geographic territory.

→  Names and contact information of all founding members (minimum four).

→  Brief description of the local market and why an IWIRC network would be successful.

→  Proposed launch timeline.

☐  Download the Network Rules of Operation template from the IWIRC website Resources/Documents section.

☐  Review and customize the Network Rules of Operation for your network’s preferences, including:

→  Local board structure (Chair, Vice Chair, Secretary, Treasurer, and any additional positions).

→  Frequency and format of board and general membership meetings.

→  Local event types and programming goals.

→  Membership dues structure (within IWIRC International guidelines).

☐  Have founding members review and approve the draft Rules of Operation before submission.

Step 5: Submit to IWIRC

☐  Submit completed Network Proposal to the IWIRC Administrative Director (ccschnapp@iwirc.com).

☐  Submit completed Network Rules of Operation together with the Proposal.

☐  Follow up with IWIRC to confirm receipt and ask about the expected review timeline.

→  The Proposal and Rules of Operation are reviewed by the IWIRC Executive Board, which may approve or request clarifications.

☐  Respond promptly to any questions or requests for additional information from the Executive Board.

| PHASE 3 | Post-Approval: Administrative Setup | Weeks 1–6 After Approval |
| --- | --- | --- |

Step 6: Tax & Financial Setup

☐  Apply for a U.S. Employer Identification Number (EIN) via the IRS.

→  EIN application: irs.gov/businesses/small-businesses-self-employed/get-an-employer-identification-number. The EIN is required to open a bank account and file annual tax returns.

☐  Open a dedicated network bank account.

→  Both the network Chair and Treasurer should sign the signature card. Contact the Administrative Director (ccschnapp@iwirc.com) for bank recommendations.

☐  Obtain any required local tax-exempt status (e.g., state tax exemption in the U.S., or equivalent in your jurisdiction).

☐  Establish a basic bookkeeping system to track income (dues, event revenue) and expenses (event costs, administrative costs).

→  Retain all financial records. Annual tax filings (Form 990 series in the U.S.) will be required. Review reporting instructions provided by IWIRC.

☐  Review and understand IWIRC’s instructions on:

→  Reporting requirements to IWIRC (periodic financial and membership reports).

→  Annual tax return filings applicable to your network.

→  Conflict of interest policy — all board members must sign the IWIRC Conflict of Interest form. Obtain the form from the Administrative Director and collect signed copies from all board members.

☐  Apply for the New Network Grant.

→  IWIRC offers a grant to help defray startup costs for new networks. Request the application form from the Administrative Director (ccschnapp@iwirc.com) and submit promptly after approval.

Step 7: Digital & Communications Setup

☐  Receive your IWIRC-provided email address and login credentials from IWIRC.

→  Follow the Exchange Online instructions provided by IWIRC to complete registration and configure your network email account.

☐  Create social media accounts (LinkedIn, Instagram, etc.) using the IWIRC-provided email address.

→  Follow all existing IWIRC networks and IWIRC International to build your audience. Review the official IWIRC Social Media Presence Guidelines before posting.

☐  Familiarize yourself with IWIRC’s brand standards, including:

→  Logo usage guidelines — available in the Resources section of iwirc.com. Only use approved logos and formats.

→  Brand color palette, typography, and tone of voice.

→  Proper use of the IWIRC name and taglines.

☐  Submit a network page header photo and brief network description to the IWIRC Membership Services Director (sfarmer@iwirc.com) for your network webpage on iwirc.com.

☐  Designate a network vendor and two (2) network admins for editing your webpage on the IWIRC website.

→  Review the website FAQs provided by IWIRC and complete the vendor/admin designation process.

☐  Access the IWIRC member directory and confirm your founding members are properly listed.

Step 8: Insurance & Compliance

☐  Locate IWIRC’s insurance information in the Resources section of the iwirc.com member portal.

☐  Review the scope of IWIRC International’s umbrella insurance coverage and determine whether any supplemental local coverage is needed.

☐  Distribute the Conflict of Interest Policy to all board members and collect signed acknowledgment forms.

☐  Review IWIRC’s bylaws (available in the Resources section of iwirc.com) to ensure your network rules align with international requirements.

| PHASE 4 | Launch Planning & Membership Build | Weeks 4–10 After Approval |
| --- | --- | --- |

Step 9: Board Formation & Initial Planning Meeting

☐  Schedule and hold an organizational meeting of founding members to formally vote in the network board.

→  Typical positions: Chair, Vice Chair, Secretary, Treasurer, and at-large board members. Consult your Rules of Operation for required positions.

☐  Establish board member terms, meeting cadence, and committee structure.

→  Common committees: Programming/Events, Membership, Communications/Marketing, Sponsorship, and Mentoring.

☐  Brainstorm ideas for the network launch event at the organizational meeting.

☐  Share the proposed launch date and event concepts with the Administrative Director (ccschnapp@iwirc.com).

☐  Assign board members to lead key workstreams (events, membership outreach, social media, sponsorship).

☐  Set up a shared communications channel (e.g., email list, group chat) for board coordination.

Step 10: Membership Enrollment

☐  Submit a complete list of founding members and board members to the IWIRC Membership Services Director (sfarmer@iwirc.com) for listing on the IWIRC website.

→  Existing IWIRC members will be transferred to the new network. New members must register at iwirc.com and select the new network.

☐  Develop a membership recruitment plan, including:

→  Target list of prospective members (attorneys, bankers, accountants, turnaround managers, financial advisors, etc.).

→  Personalized outreach messages highlighting local network benefits.

→  A plan to leverage existing IWIRC member relationships for warm introductions.

☐  Create a simple one-page or email overview of the new network for outreach purposes.

☐  Consider whether student or emerging-professional membership tiers are a priority for your network.

☐  Track membership commitments and follow up with prospects before the launch event.

Step 11: Sponsorship Outreach

☐  Identify potential local or regional sponsors (law firms, financial institutions, consulting firms).

☐  Develop a simple sponsorship proposal or menu of sponsorship opportunities.

→  Align with IWIRC’s sponsorship guidelines before approaching sponsors.

☐  Secure at least one launch event sponsor if possible, to offset startup costs.

| PHASE 5 | Network Launch | Weeks 8–14 After Approval |
| --- | --- | --- |

Step 12: Launch Event Planning

☐  Select a launch event date, venue, and format (cocktail reception, dinner, panel discussion, etc.).

☐  Confirm venue logistics: capacity, A/V, catering, accessibility.

☐  Develop a guest list that includes founding members, prospects, and local insolvency & restructuring community contacts.

☐  Plan programming for the event (e.g., welcome remarks, brief overview of IWIRC, networking time).

☐  Prepare event registration (via the IWIRC website or a platform consistent with IWIRC guidelines).

☐  Send invitations at least 4–6 weeks in advance; send reminders 1–2 weeks before the event.

Step 13: Pre-Launch Publicity

☐  Submit a quote for the IWIRC press release announcing the new network to the Membership Services Director (sfarmer@iwirc.com).

→  IWIRC International will distribute a press release to all IWIRC members globally. Review example press releases on the IWIRC website for guidance.

☐  Coordinate timing of the press release with your launch event.

☐  Share the network launch on social media and encourage founding members to amplify the announcement.

☐  Notify relevant local bar associations, professional organizations, and industry media of the new network launch.

☐  Consider issuing your own local press release or announcement to regional legal/financial trade publications.

Step 14: Launch Event Execution

☐  Confirm all logistics 48 hours before the event (venue, catering, A/V, printed materials).

☐  Prepare name badges, sign-in sheets, and any printed materials about IWIRC membership.

☐  Designate a board member to greet guests, manage sign-ins, and collect contact information from non-members.

☐  Capture photos and video (with attendee consent) for use in post-event communications and social media.

☐  Collect feedback from attendees after the event.

| PHASE 6 | Ongoing Operations — First Year | Months 3–12 |
| --- | --- | --- |

Step 15: Programming & Events

☐  Develop an annual programming calendar with at least 3–4 events in the first year.

→  Event formats may include: networking receptions, CLE/CPD panels, joint events with other bar associations, mentoring roundtables, and participation in IWIRC regional and international conferences.

☐  Submit event listings to IWIRC for inclusion on the iwirc.com calendar.

☐  Explore co-hosting events with other IWIRC networks (especially nearby networks) to broaden reach.

☐  Plan at least one educational/professional development program in the first year.

Step 16: Membership Retention & Growth

☐  Send a welcome communication to all new members after the launch event.

☐  Establish a mentoring program pairing new members with more senior practitioners.

☐  Conduct annual membership renewal outreach and track renewal rates.

☐  Solicit member feedback on programming and network activities at least annually.

☐  Identify and nominate deserving members for IWIRC International awards (Woman of the Year, Founders’ Award, etc.).

Step 17: International Engagement

☐  Register and encourage member attendance at the annual IWIRC Leadership Summit and Flagship International Conference.

☐  Engage with IWIRC International committees and working groups to represent your network at the global level.

☐  Share your network’s news, events, and member achievements with IWIRC for inclusion in global communications.

☐  Explore opportunities to participate in IWIRC’s Speakers’ Bureau and other international visibility programs.

Step 18: Ongoing Compliance & Reporting

☐  File annual tax returns (Form 990-N, 990-EZ, or 990 in the U.S., or local equivalent) by the applicable deadline.

☐  Submit periodic financial and membership reports to IWIRC as required.

☐  Renew any required local registrations or licenses annually.

☐  Update board member information with IWIRC after each annual election.

☐  Ensure all new board members sign the Conflict of Interest Policy form.

☐  Review and update your Network Rules of Operation as needed (requires IWIRC approval for material changes).

Key IWIRC Contacts

| Role | Responsibility | Contact |
| --- | --- | --- |
| Administrative Director | General inquiries, network startup resources & documents, bank recommendations, New Network Grant application, launch date coordination | ccschnapp@iwirc.com |
| Membership Services Director | Network webpage setup, member listings, press release distribution and quotes | sfarmer@iwirc.com |
| IWIRC Executive Board | Final approval of Network Proposal and Rules of Operation | Via Administrative Director |

Resources available at iwirc.com (member login required): Network Proposal template • Network Rules of Operation template • IWIRC Bylaws • Logo & Brand Guidelines • Social Media Guidelines • Conflict of Interest Policy & Form • Insurance Information • New Network Grant Application • Website FAQ